## 1_CalcSheet
[8 empty] | MS Type | Preparation | Coding | /Testing | Comments Received
[8 empty] | A | 10% | 70% | 15% | 5%
[8 empty] | B | 30% | 70%
Insert rows above this line.
| DASH ENGINEERING PHILS., INC. | LEGEND: | Delayed
| JOB NO.: JOB NAME |  | Completed on schedule
| 2021-11-12 |  | Completed but delayed. | [5 empty] | ORIGINAL PLAN DATES |  |  |  | FORECAST DATES |  |  |  | ACTUAL DATES |  |  |  | REMARKS
| WBS | Document No | Document Title | Budget MH | Weight % | Plan Prog | Act Prog | MS Type | MS - 1 | MS - 2 | MS - 3 | MS - 4 | MS - 1 | MS - 2 | MS - 3 | MS - 4 | MS - 1 | MS - 2 | MS - 3 | MS - 4
[8 empty] | A | 10% | 70% | 15% | 5% | 10% | 70% | 15% | 5% | 10% | 70% | 15% | 5%
[8 empty] | B | 30% | 70% |  |  | 30% | 70% |  |  | 30% | 70% |  |  |  | CUT-OFF | 2021-10-15 | 2021-10-22 | 2021-10-29 | 2021-11-05 | 2021-11-12 | 2021-11-19 | 2021-11-26 | 2021-12-03 | 2021-12-10 | 2021-12-17 | 2021-12-24 | 2021-12-31 | 2022-01-07 | 2022-01-14 | 2022-01-21 | 2022-01-28 | 2022-02-04 | 2022-02-11 | 2022-02-18 | 2022-02-25 | 2022-03-04 | 2022-03-11 | 2022-03-18 | 2022-03-25 | 2022-04-01 | 2022-04-08 | 2022-04-15 | 2022-04-22 | 2022-04-29 | 2022-05-06 | 2022-05-13 | 2022-05-20 | 2022-05-27 | PLAN |  | 2021-10-15 | 2021-10-22 | 2021-10-29 | 2021-11-05 | 2021-11-12 | 2021-11-19 | 2021-11-26 | 2021-12-03 | 2021-12-10 | 2021-12-17 | 2021-12-24 | 2021-12-31 | 2022-01-07 | 2022-01-14 | 2022-01-21 | 2022-01-28 | 2022-02-04 | 2022-02-11 | 2022-02-18 | 2022-02-25 | 2022-03-04 | 2022-03-11 | 2022-03-18 | 2022-03-25 | 2022-04-01 | 2022-04-08 | 2022-04-15 | 2022-04-22 | 2022-04-29 | 2022-05-06 | 2022-05-13 | 2022-05-20 | 2022-05-27 | FORECAST |  | 2021-10-15 | 2021-10-22 | 2021-10-29 | 2021-11-05 | 2021-11-12 | 2021-11-19 | 2021-11-26 | 2021-12-03 | 2021-12-10 | 2021-12-17 | 2021-12-24 | 2021-12-31 | 2022-01-07 | 2022-01-14 | 2022-01-21 | 2022-01-28 | 2022-02-04 | 2022-02-11 | 2022-02-18 | 2022-02-25 | 2022-03-04 | 2022-03-11 | 2022-03-18 | 2022-03-25 | 2022-04-01 | 2022-04-08 | 2022-04-15 | 2022-04-22 | 2022-04-29 | 2022-05-06 | 2022-05-13 | 2022-05-20 | 2022-05-27 | ACTUAL
| OVERALL PROGRESS |  |  | 811.5 | 100% | 22.14% | 27.23% |  | 12 | 7 | 0 | 0 | 12 | 7 | 0 | 0 | 14 | 10 | 0 | 0 |  | OPP | 2.884% | 9.612% | 16.42% | 18.35% | 22.14% | 28.02% | 33.65% | 37.76% | 40.07% | 45.15% | 48.6% | 48.6% | 52% | 57.47% | 62.32% | 66.1% | 68.92% | 74.23% | 79.16% | 83.7% | 87.59% | 98.03% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | OAF | 2.884% | 9.612% | 16.42% | 18.35% | 22.14% | 28.02% | 33.65% | 37.76% | 40.07% | 45.15% | 48.6% | 48.6% | 52% | 57.47% | 62.32% | 66.1% | 68.92% | 74.23% | 79.16% | 83.7% | 87.59% | 98.03% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | OAA | 2.884% | 10.11% | 15.51% | 20.99% | 27.23% | 27.23% | 27.23% | 27.23% | 27.23% | 27.23% | 27.23% | 27.23% | 27.23% | 27.23% | 27.23% | 27.23% | 27.23% | 27.23% | 27.23% | 27.23% | 27.23% | 27.23% | 27.23% | 27.23% | 27.23% | 27.23% | 27.23% | 27.23% | 27.23% | 27.23% | 27.23% | 27.23% | 27.23%
| REQUEST |  |  | 811.5 | 100% | 22.14% | 27.23% |  | 12 | 7 | 0 | 0 | 12 | 7 | 0 | 0 | 14 | 10 | 0 | 0 |  | CP | 2.884% | 9.612% | 16.42% | 18.35% | 22.14% | 28.02% | 33.65% | 37.76% | 40.07% | 45.15% | 48.6% | 48.6% | 52% | 57.47% | 62.32% | 66.1% | 68.92% | 74.23% | 79.16% | 83.7% | 87.59% | 98.03% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | CF | 2.884% | 9.612% | 16.42% | 18.35% | 22.14% | 28.02% | 33.65% | 37.76% | 40.07% | 45.15% | 48.6% | 48.6% | 52% | 57.47% | 62.32% | 66.1% | 68.92% | 74.23% | 79.16% | 83.7% | 87.59% | 98.03% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | CA | 2.884% | 10.11% | 15.51% | 20.99% | 27.23% | 27.23% | 27.23% | 27.23% | 27.23% | 27.23% | 27.23% | 27.23% | 27.23% | 27.23% | 27.23% | 27.23% | 27.23% | 27.23% | 27.23% | 27.23% | 27.23% | 27.23% | 27.23% | 27.23% | 27.23% | 27.23% | 27.23% | 27.23% | 27.23% | 27.23% | 27.23% | 27.23% | 27.23%
| REPORT CUSTOMIZATION |  |  | 442.5 | 54.53% | 37.01% | 46.35% |  | 10 | 7 | 0 | 0 | 10 | 7 | 0 | 0 | 12 | 10 | 0 | 0 |  | C2P | 5.288% | 17.63% | 26.53% | 30.06% | 37.01% | 47.8% | 58.11% | 65.65% | 65.65% | 65.65% | 65.65% | 65.65% | 65.65% | 65.65% | 69.11% | 76.05% | 81.22% | 90.96% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | C2F | 5.288% | 17.63% | 26.53% | 30.06% | 37.01% | 47.8% | 58.11% | 65.65% | 65.65% | 65.65% | 65.65% | 65.65% | 65.65% | 65.65% | 69.11% | 76.05% | 81.22% | 90.96% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | C2A | 5.288% | 18.54% | 28.45% | 34.9% | 46.35% | 46.35% | 46.35% | 46.35% | 46.35% | 46.35% | 46.35% | 46.35% | 46.35% | 46.35% | 46.35% | 46.35% | 46.35% | 46.35% | 46.35% | 46.35% | 46.35% | 46.35% | 46.35% | 46.35% | 46.35% | 46.35% | 46.35% | 46.35% | 46.35% | 46.35% | 46.35% | 46.35% | 46.35%
|  | - | Clients Requirements and Preparation | 78 | 17.63% | 100% | 100% | B | 2021-10-04 | 2021-10-22 |  |  | 2021-10-04 | 2021-10-22 |  |  | 2021-10-15 | 2021-10-22 |  |  |  |  | 30% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 30% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 30% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
P | MACRO | CR-001 | On-The-Fly items | 13.5 | 3.051% | 100% | 100% | B | 2021-10-25 | 2021-10-26 |  |  | 2021-10-25 | 2021-10-26 |  |  | 2021-10-22 | 2021-10-26 |  |  |  |  | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 30% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
P | MACRO | CR-002 | Pipe Flow U-Shape | 23.8333 | 5.386% | 0% | 0% | B | 2021-11-26 | 2021-12-03 |  |  | 2021-11-26 | 2021-12-03 | [8 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 30% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 30% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
P | MACRO | CR-003 | Pipe Flow N-Shape | 23.8333 | 5.386% | 0% | 0% | B | 2021-11-26 | 2021-12-03 |  |  | 2021-11-26 | 2021-12-03 | [8 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 30% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 30% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MACRO | CR-004 | Rotameter Direction | 15.3333 | 3.465% | 0% | 0% | B | 2022-01-20 | 2022-01-21 |  |  | 2022-01-20 | 2022-01-21 | [8 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
P | MACRO | CR-005 | Pipe Nozzle Insulation | 11.8333 | 2.674% | 100% | 100% | B | 2021-10-27 | 2021-10-28 |  |  | 2021-10-27 | 2021-10-28 |  |  | 2021-10-26 | 2021-10-26 |  |  |  |  | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| MACRO | CR-006 | Incorrect Support Component Part | 15.3333 | 3.465% | 0% | 0% | B | 2022-01-26 | 2022-01-27 |  |  | 2022-01-26 | 2022-01-27 | [8 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MACRO | CR-007 | Support Span | 15.3333 | 3.465% | 0% | 0% | B | 2022-01-26 | 2022-01-27 |  |  | 2022-01-26 | 2022-01-27 | [8 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
P | MACRO | CR-008 | Pipe Cut Length | 16 | 3.616% | 0% | 30% | B | 2021-11-16 | 2021-11-19 |  |  | 2021-11-16 | 2021-11-19 |  |  | 2021-11-11 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 0% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30%
| MACRO | CR-009 | Spiral Gasket | 15.3333 | 3.465% | 0% | 0% | B | 2022-02-01 | 2022-02-03 |  |  | 2022-02-01 | 2022-02-03 | [8 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MACRO | CR-010 | Gusset Requirement | 25.1667 | 5.687% | 0% | 0% | B | 2022-02-03 | 2022-02-07 |  |  | 2022-02-03 | 2022-02-07 | [8 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 30% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 30% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MACRO | CR-011 | Duplicated Support Components | 10.5 | 2.373% | 0% | 0% | B | 2022-02-09 | 2022-02-10 |  |  | 2022-02-09 | 2022-02-10 | [8 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
P | MACRO | CR-012 | Check Connections of Slip On Flange | 12.3333 | 2.787% | 100% | 100% | B | 2021-10-29 | 2021-11-08 |  |  | 2021-10-29 | 2021-11-08 |  |  | 2021-10-27 | 2021-11-05 |  |  |  |  | 0% | 0% | 30% | 30% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 30% | 30% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 30% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
P | MACRO | CR-013 | Piperun Name Rule | 14.1667 | 3.202% | 30% | 100% | B | 2021-11-11 | 2021-11-15 |  |  | 2021-11-11 | 2021-11-15 |  |  | 2021-11-02 | 2021-11-12 |  |  |  |  | 0% | 0% | 0% | 0% | 30% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 0% | 30% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 30% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
P | MACRO | CR-014 | Pipe Component Name Rule | 14.1667 | 3.202% | 30% | 100% | B | 2021-11-11 | 2021-11-15 |  |  | 2021-11-11 | 2021-11-15 |  |  | 2021-11-08 | 2021-11-12 |  |  |  |  | 0% | 0% | 0% | 0% | 30% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 0% | 30% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
P | MACRO | CR-015 | Insulation Spec Rule | 12.1667 | 2.75% | 100% | 100% | B | 2021-10-29 | 2021-11-08 |  |  | 2021-10-29 | 2021-11-08 |  |  | 2021-10-27 | 2021-10-28 |  |  |  |  | 0% | 0% | 30% | 30% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 30% | 30% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
P | MACRO | CR-016 | Base Plate Type Not Set | 16 | 3.616% | 0% | 30% | B | 2021-11-22 | 2021-11-23 |  |  | 2021-11-22 | 2021-11-23 |  |  | 2021-11-11 | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 0% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30%
P | MACRO | CR-017 | Route Part Notes Input | 15.3333 | 3.465% | 0% | 0% | B | 2021-11-22 | 2021-11-26 |  |  | 2021-11-22 | 2021-11-26 | [8 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
P | MACRO | CR-018 | Instrument Orientation | 11.1667 | 2.524% | 100% | 100% | B | 2021-10-29 | 2021-11-05 |  |  | 2021-10-29 | 2021-11-05 |  |  | 2021-10-27 | 2021-11-05 |  |  |  |  | 0% | 0% | 30% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 30% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 30% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
P | MACRO | CR-019 | Steam Trap Orientation | 11.1667 | 2.524% | 100% | 100% | B | 2021-10-29 | 2021-11-02 |  |  | 2021-10-29 | 2021-11-02 |  |  | 2021-10-27 | 2021-11-03 |  |  |  |  | 0% | 0% | 30% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 30% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 30% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| MACRO | CR-020 | Weld Support Clash | 15 | 3.39% | 0% | 0% | B | 2022-02-09 | 2022-02-10 |  |  | 2022-02-09 | 2022-02-10 | [8 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MACRO | CR-021 | Weld Support Clearance | 15 | 3.39% | 0% | 0% | B | 2022-02-15 | 2022-02-16 |  |  | 2022-02-15 | 2022-02-16 | [8 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| MACRO | CR-022 | Hole Management | 25 | 5.65% | 0% | 0% | B | 2022-02-17 | 2022-02-18 |  |  | 2022-02-17 | 2022-02-18 | [8 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
P | MACRO | CR-023 | Head to head component Checking | 17 | 3.842% | 30% | 100% | B | 2021-11-08 | 2021-11-14 |  |  | 2021-11-08 | 2021-11-14 |  |  | 2021-11-08 | 2021-11-12 |  |  |  |  | 0% | 0% | 0% | 0% | 30% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 0% | 30% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
insert rows above this line.
| ADMINISTRATIVE DOCUMENTATION |  |  | 369 | 45.47% | 4.309% | 4.309% |  | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | C3P | 0% | 0% | 4.309% | 4.309% | 4.309% | 4.309% | 4.309% | 4.309% | 9.404% | 20.57% | 28.16% | 28.16% | 35.64% | 47.67% | 54.17% | 54.17% | 54.17% | 54.17% | 54.17% | 64.15% | 72.71% | 95.66% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | C3F | 0% | 0% | 4.309% | 4.309% | 4.309% | 4.309% | 4.309% | 4.309% | 9.404% | 20.57% | 28.16% | 28.16% | 35.64% | 47.67% | 54.17% | 54.17% | 54.17% | 54.17% | 54.17% | 64.15% | 72.71% | 95.66% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | C3A | 0% | 0% | 0% | 4.309% | 4.309% | 4.309% | 4.309% | 4.309% | 4.309% | 4.309% | 4.309% | 4.309% | 4.309% | 4.309% | 4.309% | 4.309% | 4.309% | 4.309% | 4.309% | 4.309% | 4.309% | 4.309% | 4.309% | 4.309% | 4.309% | 4.309% | 4.309% | 4.309% | 4.309% | 4.309% | 4.309% | 4.309% | 4.309%
| DOCUMENT | CR-001 | On-The-Fly items - Administrative Documentation | 14 | 3.794% | 0% | 0% | B | 2021-12-07 | 2021-12-09 |  |  | 2021-12-07 | 2021-12-09 | [8 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| DOCUMENT | CR-002 | Pipe Nozzle Insulation - Administrative Documentation | 16 | 4.336% | 0% | 0% | B | 2021-12-10 | 2021-12-13 |  |  | 2021-12-10 | 2021-12-13 | [8 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 30% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 30% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| DOCUMENT | CR-003 | Insulation Spec Rule - Administrative Documentation | 16 | 4.336% | 0% | 0% | B | 2021-12-14 | 2021-12-15 |  |  | 2021-12-14 | 2021-12-15 | [8 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| DOCUMENT | CR-004 | Steam Trap Orientation - Administrative Documentation | 16 | 4.336% | 0% | 0% | B | 2022-02-21 | 2022-02-24 |  |  | 2022-02-21 | 2022-02-24 | [8 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| DOCUMENT | CR-005 | Instrument Orientation - Administrative Documentation | 14 | 3.794% | 0% | 0% | B | 2021-12-16 | 2021-12-17 |  |  | 2021-12-16 | 2021-12-17 | [8 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| DOCUMENT | CR-006 | Check Connections of Slip On Flange - Administrative Documentation | 16 | 4.336% | 0% | 0% | B | 2022-02-23 | 2022-02-24 |  |  | 2022-02-23 | 2022-02-24 | [8 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| DOCUMENT | CR-007 | Piperun Name Rule - Administrative Documentation | 16 | 4.336% | 0% | 0% | B | 2022-02-24 | 2022-03-11 |  |  | 2022-02-24 | 2022-03-11 | [8 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 30% | 30% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 30% | 30% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| DOCUMENT | CR-008 | Pipe Component Name Rule - Administrative Documentation | 16 | 4.336% | 0% | 0% | B | 2021-12-20 | 2021-12-21 |  |  | 2021-12-20 | 2021-12-21 | [8 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| DOCUMENT | CR-009 | Head to head component Checking - Administrative Documentation | 16 | 4.336% | 0% | 0% | B | 2022-02-28 | 2022-03-01 |  |  | 2022-02-28 | 2022-03-01 | [8 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| DOCUMENT | CR-010 | Pipe Cut Length - Administrative Documentation | 16 | 4.336% | 0% | 0% | B | 2022-03-15 | 2022-03-16 |  |  | 2022-03-15 | 2022-03-16 | [8 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| DOCUMENT | CR-011 | Pipe Flow U-Shape - Administrative Documentation | 12 | 3.252% | 0% | 0% | B | 2022-03-02 | 2022-03-03 |  |  | 2022-03-02 | 2022-03-03 | [8 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| DOCUMENT | CR-012 | Pipe Flow N-Shape - Administrative Documentation | 12 | 3.252% | 0% | 0% | B | 2021-12-22 | 2021-12-23 |  |  | 2021-12-22 | 2021-12-23 | [8 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| DOCUMENT | CR-013 | Route Part Notes Input - Administrative Documentation | 12 | 3.252% | 0% | 0% | B | 2022-01-03 | 2022-01-04 |  |  | 2022-01-03 | 2022-01-04 | [8 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| DOCUMENT | CR-014 | Base Plate Type Not Set - Administrative Documentation | 12 | 3.252% | 0% | 0% | B | 2022-01-05 | 2022-01-06 |  |  | 2022-01-05 | 2022-01-06 | [8 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| DOCUMENT | CR-015 | Incorrect Support Component Part - Administrative Documentation | 12 | 3.252% | 0% | 0% | B | 2022-01-07 | 2022-01-10 |  |  | 2022-01-07 | 2022-01-10 | [8 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 30% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 30% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| DOCUMENT | CR-016 | Rotameter Direction - Administrative Documentation | 12 | 3.252% | 0% | 0% | B | 2022-01-10 | 2022-01-11 |  |  | 2022-01-10 | 2022-01-11 | [8 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| DOCUMENT | CR-017 | Gusset Requirement - Administrative Documentation | 12 | 3.252% | 0% | 0% | B | 2022-01-12 | 2022-01-13 |  |  | 2022-01-12 | 2022-01-13 | [8 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| DOCUMENT | CR-018 | Duplicated Support Components - Administrative Documentation | 12 | 3.252% | 0% | 0% | B | 2022-01-14 | 2022-01-14 |  |  | 2022-01-14 | 2022-01-14 | [8 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| DOCUMENT | CR-019 | Support Span - Administrative Documentation | 12 | 3.252% | 0% | 0% | B | 2022-01-17 | 2022-01-18 |  |  | 2022-01-17 | 2022-01-18 | [8 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| DOCUMENT | CR-020 | Weld Support Clash - Administrative Documentation | 12 | 3.252% | 0% | 0% | B | 2022-03-04 | 2022-03-11 |  |  | 2022-03-04 | 2022-03-11 | [8 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 30% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 30% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| DOCUMENT | CR-021 | Weld Support Clearance - Administrative Documentation | 12 | 3.252% | 0% | 0% | B | 2022-03-08 | 2022-03-09 |  |  | 2022-03-08 | 2022-03-09 | [8 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| DOCUMENT | CR-022 | Hole Management - Administrative Documentation | 16 | 4.336% | 0% | 0% | B | 2022-03-10 | 2022-03-11 |  |  | 2022-03-10 | 2022-03-11 | [8 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| DOCUMENT | CR-023 | Spiral Gasket - Administrative Documentation | 12 | 3.252% | 0% | 0% | B | 2022-01-20 | 2022-01-21 |  |  | 2022-01-20 | 2022-01-21 | [8 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| LOE |  | Meeting | 30 | 8.13% | 30% | 30% | B | 2021-10-25 | 2022-03-09 |  |  | 2021-10-25 | 2022-03-09 |  |  | 2021-11-05 | [5 empty] | 0% | 0% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30%
| LOE |  | Weekly Report | 23 | 6.233% | 30% | 30% | B | 2021-10-25 | 2022-03-09 |  |  | 2021-10-25 | 2022-03-09 |  |  | 2021-11-05 | [5 empty] | 0% | 0% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0% | 0% | 0% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30%
insert rows above this line.
P | Priority
s

## 2_S-Curve(s)
DASH ENGINEERING PHILS., INC.
JOB NO.: JOB NAME
2021-11-12
1) Schedule Summary
[26 empty] | Project Duration: |  | Forecasted Duration | -
[26 empty] | Planned Completion Date: | 2022-03-11 | Forecasted Completion | #VALUE!
[26 empty] | Variance to Date: |  | Variance at Completion | #VALUE!
[25 empty] | 2) Progress Summary |  |  | 3) MH Summary
[25 empty] | Plan % |  | #N/A | Budget MH
[25 empty] | Actual % |  | 27.23% | Actual MH
[28 empty] | Actual MH % | #DIV/0!
[28 empty] | Forecast Completion MH | #N/A
[28 empty] | Variance at Completion MH | #N/A
| 2021-10-15 | 2021-10-22 | 2021-10-29 | 2021-11-05 | 2021-11-12 | 2021-11-19 | 2021-11-26 | 2021-12-03 | 2021-12-10 | 2021-12-17 | 2021-12-24 | 2021-12-31 | 2022-01-07 | 2022-01-14 | 2022-01-21 | 2022-01-28 | 2022-02-04 | 2022-02-11 | 2022-02-18 | 2022-02-25 | 2022-03-04 | 2022-03-11 | 2022-03-18 | 2022-03-25
Plan Progress Inc | 2.884% | 6.728% | 6.812% | 1.926% | 3.789% | 5.882% | 5.623% | 4.112% | 2.317% | 5.077% | 3.45% | 0% | 3.401% | 5.471% | 4.847% | 3.779% | 2.82% | 5.313% | 4.929% | 4.535% | 3.894% | 10.44% | 1.972% | 0%
Plan Progress Cum | 2.884% | 9.612% | 16.42% | 18.35% | 22.14% | 28.02% | 33.65% | 37.76% | 40.07% | 45.15% | 48.6% | 48.6% | 52% | 57.47% | 62.32% | 66.1% | 68.92% | 74.23% | 79.16% | 83.7% | 87.59% | 98.03% | 100% | 100%
Fcast Progress Inc | 2022-01-21: 2.458%; 2022-01-28: 3.779%; 2022-02-04: 2.82%; 2022-02-11: 5.313%; 2022-02-18: 4.929%; 2022-02-25: 4.535%; 2022-03-04: 3.894%; 2022-03-11: 10.44%; 2022-03-18: 1.972%; 2022-03-25: 0%
Fcast Progress Cum | 2022-01-21: 62.32%; 2022-01-28: 66.1%; 2022-02-04: 68.92%; 2022-02-11: 74.23%; 2022-02-18: 79.16%; 2022-02-25: 83.7%; 2022-03-04: 87.59%; 2022-03-11: 98.03%; 2022-03-18: 100%; 2022-03-25: 100%
Act Progress Inc | 2.884% | 7.227% | 5.404% | 5.473% | 6.246% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Act Progress Cum | 2.884% | 10.11% | 15.51% | 20.99% | 27.23% | 27.23% | 27.23% | 27.23% | 27.23% | 27.23% | 27.23% | 27.23% | 27.23% | 27.23% | 27.23%
MH A- Inc | 0% | 2.187% | 2.973% | 3.87% | 4.992% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
MH A- Cum | 0% | 2.187% | 5.16% | 9.03% | 14.02% | 14.02% | 14.02% | 14.02% | 14.02% | 14.02% | 14.02% | 14.02% | 14.02% | 14.02% | 14.02%
Act-Hr Expended | 2021-10-15: 0; 2021-10-22: 78; 2021-10-29: 106; 2021-11-05: 138; 2021-11-12: 178

## 3_Report
DASH ENGINEERING PHILS., INC. | [11 empty] | Report Ref. No: | DSH-MPE-R-0015
JOB NO.: JOB NAME | [11 empty] | Report Date: | 2021-10-28
PROJECT STATUS REPORT
2021-11-12 |  | Plan Progress % | Actual Progress % | Original Budget | Actual Hours Expended | MH % Consumed | TOTAL | IFA |  | IFC |  | REMARKS
OVERALL PROGRESS | #REF! | 22.14% | 27.23% | 811.5 | 177 | 21.81% | 47 | 0 | 0 | 0 | 0
REQUEST | #REF! | 22.14% | 27.23% | 811.5 | 177 | 21.81% | 0 | 0 | 0 | 0 | 0
REPORT CUSTOMIZATION | #REF! | 37.01% | 46.35% | 442.5 | 177 | 40% | 0 | 0 | 0 | 0 | 0
ADMINISTRATIVE DOCUMENTATION | #REF! | 4.309% | 4.309% | 369 | 0 | 0% | 0 | 0 | 0 | 0 | 0
2021-11-12 |  | Plan Progress % | Actual Progress % | Original Budget | Actual Hours Expended | MH % Consumed | TOTAL | IFA |  | IFC |  | REMARKS
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
Prepared By: |  | Checked By: | [9 empty] | Approved By:
Project Control LE |  | Department Leader | [9 empty] | Project Control Manager

## 4_AddlDocuments
[7 empty] | MS Type | Doc prep for 1st issue | IFA/IFR/IFI | Comments Received | Final Issue/IFC
[7 empty] | A | 10% | 70% | 15% | 5%
[7 empty] | B | 20% | 80%
Insert rows above this line.
DASH ENGINEERING PHILS., INC. | LEGEND: | Delayed
JOB NO.: JOB NAME |  | Completed on schedule
2019-09-08 |  | Completed but delayed. | [5 empty] | ORIGINAL PLAN DATES |  |  |  | FORECAST DATES |  |  |  | ACTUAL DATES |  |  |  | REMARKS
WBS | Document No | Document Title | Budget MH | Weight % | Plan Prog | Act Prog | MS Type | MS - 1 | MS - 2 | MS - 3 | MS - 4 | MS - 1 | MS - 2 | MS - 3 | MS - 4 | MS - 1 | MS - 2 | MS - 3 | MS - 4
[7 empty] | A | 10% | 70% | 15% | 5% | 10% | 70% | 15% | 5% | 10% | 70% | 15% | 5%
[7 empty] | B | 20% | 80% |  |  | 20% | 80% |  |  | 20% | 80% |  |  |  | CUT-OFF | 2019-06-02 | 2019-06-09 | 2019-06-16 | 2019-06-23 | 2019-06-30 | 2019-07-07 | 2019-07-14 | 2019-07-21 | 2019-07-28 | 2019-08-04 | 2019-08-11 | 2019-08-18 | 2019-08-25 | 2019-09-01 | 2019-09-08 | 2019-09-15 | 2019-09-22 | 2019-09-29 | 2019-10-06 | 2019-10-13 | 2019-10-20 | 2019-10-27 | 2019-11-03 | 2019-11-10 | 2019-11-17 | 2019-11-24 | 2019-12-01 | 2019-12-08 | 2019-12-15 | 2019-12-22 | 2019-12-29 | 2020-01-05 | 2020-01-12 | PLAN |  | 2019-06-02 | 2019-06-09 | 2019-06-16 | 2019-06-23 | 2019-06-30 | 2019-07-07 | 2019-07-14 | 2019-07-21 | 2019-07-28 | 2019-08-04 | 2019-08-11 | 2019-08-18 | 2019-08-25 | 2019-09-01 | 2019-09-08 | 2019-09-15 | 2019-09-22 | 2019-09-29 | 2019-10-06 | 2019-10-13 | 2019-10-20 | 2019-10-27 | 2019-11-03 | 2019-11-10 | 2019-11-17 | 2019-11-24 | 2019-12-01 | 2019-12-08 | 2019-12-15 | 2019-12-22 | 2019-12-29 | 2020-01-05 | 2020-01-12 | FORECAST |  | 2019-06-02 | 2019-06-09 | 2019-06-16 | 2019-06-23 | 2019-06-30 | 2019-07-07 | 2019-07-14 | 2019-07-21 | 2019-07-28 | 2019-08-04 | 2019-08-11 | 2019-08-18 | 2019-08-25 | 2019-09-01 | 2019-09-08 | 2019-09-15 | 2019-09-22 | 2019-09-29 | 2019-10-06 | 2019-10-13 | 2019-10-20 | 2019-10-27 | 2019-11-03 | 2019-11-10 | 2019-11-17 | 2019-11-24 | 2019-12-01 | 2019-12-08 | 2019-12-15 | 2019-12-22 | 2019-12-29 | 2020-01-05 | 2020-01-12 | ACTUAL
OVERALL PROGRESS |  |  | 0 | #DIV/0! | #DIV/0! | #DIV/0! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | OPP | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | OAF | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | OAA | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
PROCESS |  |  | 0 | #DIV/0! | #DIV/0! | #DIV/0! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | CP | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | CF | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | CA | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
PROCESS D/S HEAT EXCHANGERS |  |  | 0 | #DIV/0! | 0% | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | C1P | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | C1F | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | C1A | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
PROCESS D/S PUMPS |  |  | 0 | #DIV/0! | 0% | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | C2P | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | C2F | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | C2A | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
PROCESS D/S COMP&BLOWERS |  |  | 0 | #DIV/0! | #VALUE! | #VALUE! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | C3P | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | C3F | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | C3A | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
PROCESS D/S DRUMS |  |  | 0 | #DIV/0! | 0% | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | C5P | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | C5F | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | C5A | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
EQUIPMENT |  |  | 0 | #DIV/0! | #DIV/0! | #DIV/0! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Q1P | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | Q1F | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | Q1A | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
REACTOR |  |  | 0 | #DIV/0! | #VALUE! | #VALUE! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Q2P | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | Q2F | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | Q2A | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
AGITATOR |  |  | 0 | #DIV/0! | #VALUE! | #VALUE! |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Q3P | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | Q3F | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! |  | Q3A | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
s